## Table 1
[8 empty] | ISSUE 8 |  | 2026-03-01 | (Please refer to Sustainability or Students' Union Webpages for most up to date version) |  | ACTION COMPLETED
TO BE COMPLETED
Fairtrade SMART Action Plan 2024/26
Action Number | Action | Baseline Status | Specific | Measurable | Appropriate | Realistic | Time |  | Fairtrade criteria |  |  | Who is Responsible | Status
1 - 24/26 | Renewal Meeting | Meeting planned for October 2024 to present new Smart action plan for March 2024 award submission | Reviewing criteria for Fairtrade University Award. | Actions and agenda agreed prior for upcoming steering group meeting. | MN001 | SU and University co-ordinators. | 2024-10-01 |  | MN001 - Leadership and strategy – Mandatory - The partnership has a working or co-ordinating group that meets regularly and formally leads on efforts to attain, or retain Fairtrade University and College Award status |  |  | Students' Union and Cardiff Met University | Meeting planned for October 24
2 - 24/26 | Review of University's Fairtrade Policy. | Policy approved Management Board May 2025 | Review and update policy in line with new criteria. | Policy will be updated and published publically on Sustainability and Students' Union external webpage. | MN003 / LD002 | Members of steering group able to complete. Managers and catering outlets input and approval available. | Presentation to Management Board for policy approval |  | MN003 - Leadership and strategy - Mandatory - The partnership has published a public commitment of intent to support and champion Fairtrade and its values within the last two years signed by senior management across the organisations and their retail and catering outlets. |  |  | Management Board | Policy updated and agreed by Management Board and published May 25
3 - 24/26 | Publish public commitment of intent. | Statement completed with advertisement of Fairtrade status, publication of Policy | The University and SU has a public commitment of intent that states we will support and champion Fairtrade and it's values. Signed by senior management and retail and catering outlets. | Publication of Policy, current Fairtrade status | MN003 | Can draft statement for approval by steering group, catering and retail outlets and senior management. | Every two years. |  | MN003 - Leadership and strategy - Mandatory - The partnership has published a public commitment of intent to support and champion Fairtrade and its values within the last two years signed by senior management across the organisations and their retail and |  |  | Fairtrade Steering Group | Completed
4 - 24/26 | SMART Action Plan. | Action plans Issue 1 -4 for 2022 Award submission as starting point. | Update action plan to meet specific criteria for Fairtrade award 24-26 | Creation of action plan and publish on external webpage. Review regularly | MN002 | Steering group allocated resources to agreed Action Plan. | Updated after October 24 Meeting |  | MN002 - Leadership and strategy - Mandatory - The partnership has a SMART action plan on Fairtrade and has published it. It should include operational considerations such as procurement and catering, campaigning and influencing, engagement and communications and a strong focus on the monitoring and evaluation of all activities. |  |  | Fairtrade Steering Group | Action plan created. To be updated continually and published on websites.
5 - 24/26 | Fairtrade Steering Group. | Fairtrade group meets termly. Meeting Planned for Oct 24, Feb 25, Jan 26, March 26 | Fairtrade group to re-convene and meet regularly | Agenda, minutes and attendees. Evidence to be uploaded after each meeting | MN001 | Led by Sustainability Engagement Officer, Attended by staff and students of Cardiff Met and SU. | Termly |  | MN001 - Leadership and strategy – Mandatory - The partnership has a working or co-ordinating group that meets regularly and formally leads on efforts to attain, or retain Fairtrade University and College Award status |  |  | Students' Union and Cardiff Met University | Meetings taking place twice per academic year, with ad hoc meetings closer to Fairtrade Forthnight
6 - 24/26 | Terms of Reference | Previous attendees for committee structure. | Decide who is going to be attending the committee and the targets and objectives of Environmental Management System for the Students' Union, Paper & Print, Sustainability Engagement and Sustainable Food | Implementing the actions of the SMART Action Plan. | MN001 and MN003 | Terms of Reference to be reviewed at October 2024 meeting | 2024-10-01 |  | MN001 - Leadership and strategy – Mandatory - The partnership has a working or co-ordinating group that meets regularly and formally leads on efforts to attain, or retain Fairtrade University and College Award status. MN003 - Leadership and strategy - Mandatory - The partnership has published a public commitment of intent to support and champion Fairtrade and its values within the last two years signed by senior management across the organisations and their retail and catering outlets. |  |  | Fairtrade Steering Group | Terms of reference reviewed October 2024
7 - 24/26 | Consider Fairtrade Fortnight events that can be delivered by SU / Cardiff Met Catering | Events and campaigns scheduled for 24-26 submission | Special offers, point of sale | Number of events, number of engagements, number of surveys completed | MN004 | Increase in number of events, engagements and surveys completed | October 2024 meeting agreement |  | MN004 - Campaigning and Influencing - Mandatory The partnership has held a series of events/promotions/engagement activities during Fairtrade Fortnight (February/March every year) and has measured impact across the events. |  |  | Fairtrade Steering Group | For Fairtrade Steering Group agenda
8 - 24/26 | Meeting of Steering Group to Plan Fairtrade Fortnight. | Meeting planned. | Meeting will review last years activities and to devise a survey of Fairtrade awareness on campus. Will also review ideas and budget for events for Fairtrade Fortnight or other key dates that are suitable for the univesity. | Agenda, minutes and attendees. | MN004 | Led by President of the Students' Union. Attended by staff and students of Cardiff Met and SU. | Before Fairtrade Fortnight. |  | MN004 - Campaigning and Influencing - Mandatory The partnership has held a series of events/promotions/engagement activities during Fairtrade Fortnight (February/March every year) and has measured impact across the events. |  |  | Fairtrade Steering group. | Events and campaign all discussed for 2024-2026
9 - 24/26 | Co-ordinate Comms and Marketing for Fairtrade Fortnight. | Plans for Comms and Marketing have been discussed. | Measure impact of each event, attendance, engagement and social media response | Review Instagram and website Number of attendees. Measured impact of events. | MN004 | Sustainability staff and relevant staff from SU have time set aside to plan and carry out the marketing. | Before and during Fairtrade Fortnight. |  | MN004 - Campaigning and Influencing - Mandatory The partnership has held a series of events/promotions/engagement activities during Fairtrade Fortnight (February/March every year) and has measured impact across the events. |  |  | Relevant Sustainability and SU staff. | Completed
10 - 24/26 | Consider Fairtrade Fortnight Afternoon Tea event. | No previous similar events. | A fairtrade afternoon tea event where Fairtrade ingredients will be used to make the baked goods. | Attendees and interaction with the event is measurable. Interaction with social media post also measurable. Measuring how many people we engage with, how many promotional materials are given out. | MN004 | Staff and students can participate. Event can be held on campus with the Fairtrade Steering group able to plan. | Scheduled for 11th March 2026 |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Fairtrade Steering group. | Completed
11 - 24/26 | Fairtrade Fortnight Product Tasting. | Similar events previously held | The group to organise a stall with tasting samples for staff and students to try Fairtrade food products. To try and increase awareness and interest in the products. | Interaction with stall and promotional social media posts measurable. Measuring how many people we engage with, how many promotional materials are given out. | MN004 | Event to be integrated either as part of Fairtrade Fortnight or as part of a suitable date in the university such as Green Week 2025 | During Green Week 2025 |  | MN004 - Campaigning and Influencing - Mandatory The partnership has held a series of events/promotions/engagement activities during Fairtrade Fortnight (February/March every year) and has measured impact across the events. |  |  | Sustainability Team | Delivered a stall as part of Green Week 2025
12 - 24/26 | Fairtrade Fundariser - Pre Loved Shop Pop Up supported by Business Management Students | Similar events previously held by Students' Union. | Business Management students to organise a fundraiser for Fairtrade with the help of Sustainability Team | Interaction with the events are measurable through donations and numbers of attendees, social media interaction | MN005 | Event organised by international student cohort | 2026-03-01 |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Sustainability Team in collaboration with student group | Completed
13 - 24/26 | Fairtrade Community Day | Monthly term time event for staff, students and the local community to attend | Stalll at the Community Day to raise Fairtrade Awareness and promotion of food products. To try and increase awareness and interest in the products & award. | Interaction with stall and promotional social media posts measurable. Measuring how many people we engage with, how many promotional materials are given out. | MN005 | Sustainability Team hold a Fairtrade stall at the monthly term time event. | Three times per academic year |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Sustainability Team | Complated
14 - 24/26 | Fairtrade at GO Green Week November 2025 | Students' Union stall amongst other green initiative awareness campaigns for Campus | Students' Union stall at Go Green Week to raise Fairtrade Awareness and promotion of food products. To try and increase awareness and interest in the products & award. | Interaction with stall and promotional social media posts measurable. Measuring how many people we engage with, how many promotional materials are given out. | MN005 | Students' Union in Collaboration with Sustainability Team hold a Fairtrade stall at the annual Go Green Week event. | for one week |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Sustainability Team | Completed
15 - 24/26 | Fairtrade information stand at Freshers Fayre 2025 | Expressions of interest to be collated from 1st years for prospective involvement in Fairtrade Steering Committee, Fairtrade events or a Fairtrade Society | Collate a mailing list of interested Freshers to invite them to attend termly Fairtrade Steering Group; set-up a relevant society or attend Fairtrade events. | Interaction with stall and promotional social media posts measurable. Measuring how many people we engage with, how many promotional materials are given out. | MN005 | Sustainability Team hold a Fairtrade stall at the annual Freshers Fayre event. | for one day each year |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Sustainability Team | Complated
16 - 24/26 | Each outlet to provide previous terms product range sales of Fairtrade products at each Fairtrade Steering Group meeting | October 2024 meeting will provide the baseline data | Students' Union outlets, Catering and Hospitality & Print Studio | Each outlets contribution will be added into a spreadsheet to demonstrate increase in range and sales | MN006 | Collation of spreadsheet will demonstrate increase in range and sales | At each termly meeting |  | MN006 - Procurement, Retail & Catering - Mandatory - Any retail or catering outlets owned or operated by the partnership stock Fairtrade certified products in all of the following categories, and are working to increase either the number of lines OR number of items sold year on year: • Tea • Coffee • Sugar • Hot chocolate and cocoa • Chocolate, confectionary or snacks • Cotton clothing |  |  | Fairtrade Steering Group | Completed
17 - 24/26 | Request or design new Fairtrade Media Templates and Promotion Materials for Point of sale, events and campaigns | No promotional materials. | Order promotional material from Fairtrade Foundation. | Promotional materials updated. | MN008 | Products available on Fairtrade Foundation website and all catering outlets on campus. | prior to Fairtrade Fortnight |  | MN008 - Procurement, Retail & Catering - Mandatory - There is up to date and effective Point of Sale (POS) material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade to growing communities. This POS should be clearly displayed next to the relevant products to avoid confusion, and it should be refreshed periodically. |  |  | Students' Union & Sustainability Team | Completed
18 - 24/26 | Point of sale information displays (at counters, brochures and on-line) | Point of sale information displays after updated after 2024 submission | Each Catering Outlet, SU Bar and Shop and Print Studio | Audit to be completed by March 2026 | MN008 | regular updates of point of sale signage to be provided for Fairtrade evidence with location and dates | at each Fairtrade meeting |  | MN008 - Procurement, Retail & Catering - Mandatory - There is up to date and effective Point of Sale (POS) material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade to growing communities. This POS should be clearly displayed next to the relevant products to avoid confusion, and it should be refreshed periodically. |  |  | SU Catering, Print and Catering & Hospitality Manager | Completed
19 - 24/26 | Review Hospitality Booking System Confirmation. | No indication in booking confirmations that hospitality provides Fairtrade products. | Review booking confirmation statement for hospitality to include an indication of the University's Fairtrade status. Review the possibility of each Fairtrade product declaring that they are Fairtrade. | Fairtrade information available when booking hospitality. Photos of information provided. | MN008 | Catering and hospitality manager can obtain information from suppliers. Promotional material can be obtained from Fairtrade Foundation website. | By Fairtrade Fortnight. |  | MN008 - Procurement, Retail & Catering - Mandatory - There is up to date and effective Point of Sale (POS) material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade to growing communities. This POS should be clearly displayed next to the relevant products to avoid confusion, and it should be refreshed periodically. |  |  | Catering and hospitality manager. | Completed
20 - 24/26 | Any social media activity relating to Fairtrade to be collated and forwarded for evidence | SU, Cardiff Met Catering and Sustainability social media accounts - data analysis | SU, Cardiff Met Catering and Sustainability social media accounts - data analysis - review engagements and attendee numbers if applicable | Social media engagements and attendee numbers if applicable | MN005 | Continue to engage students, staff and or the local community on or off campus to widen the reach and impact of Fairtrade events and information. | Ongoing year on year. |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Fairtrade Steering Group | Completed
21 - 24/26 | Review Fairtrade products sold in all the Cardiff Met and Students' Union catering and retail outlets. | Currently Fairtrade products are sold and promoted at both Cardiff Met and Students' Union catering and retail facilities. | Review what products from each product lines are stocked in each outlet. Determine how to increase either the number of product lines or the amount of stock sold in each outlet. | Monthly summary of stocklists from each outlet. Photos of products stocked, periodically updated. | MN006 and MN007 | Each outlet will have to be audited separately to decide what products are appropriate and how their stock can be increased in line with the University and Students' Union Guidelines. | Ongoing year on year. |  | MN006 - Procurement, Retail & Catering - Mandatory - Any retail or catering outlets owned or operated by the partnership stock Fairtrade certified products in all of the following categories, and are working to increase either the number of lines OR number of items sold year on year: • Tea • Coffee • Sugar • Hot chocolate and cocoa • Chocolate, confectionary or snacks • Cotton clothing |  |  | Catering and hospitality manager and the Students' Union Commercial Operations. | Completed
22 - 24/26 | Review cotton products. | Use 22-24 submission sales as baseline | Review whether the cotton products sold by the University and Students' Union have increased | Sales numbers from each outlet. Stock order and delivery forms. | MN006 | Cotton products are available to stock. The Fairtrade Steering Group must work with University and Students' Union outlets to decide what products would be appropriate to sell. | Before end of toolkit. |  | MN006 - Procurement, Retail & Catering - Mandatory - Any retail or catering outlets owned or operated by the partnership stock Fairtrade certified products in all of the following categories, and are working to increase either the number of lines OR number of items sold year on year: • Tea • Coffee • Sugar • Hot chocolate and cocoa • Chocolate, confectionary or snacks • Cotton clothing |  |  | Fairtrade Steering group and retail outlets and University / SU procurement, Print Studio | completed - Hoodies, t-shirts and polo's
23 - 24/26 | Review POS materials in all the Cardiff Met and Students' Union catering and retail outlets. | There is some POS information in outlets. | Review with catering and retail outlets what POS material is appropriate and coordinate with the relevant staff to ensure POS material is maintained and updated periodically. Order POS materials from Fairtrade Foundation. | Orders of POS material from Fairtrade Foundation. Measure any impact on sales or awareness. Photographs evidencing POS material. | MN008 | Each outlet will have to be audited separately to decide what POS materials are appropriate. | Ongoing year on year. |  | MN008 - Procurement, Retail & Catering - Mandatory - There is up to date and effective Point of Sale (POS) material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade to growing communities. This POS should be clearly displayed next to the relevant products to avoid confusion, and it should be refreshed periodically. |  |  | Catering and hospitality manager and the Students' Union. | Completed
24 - 24/26 | Student led innovative campaigns. | Previous event with Climate Justice Society - a quiz | Determine student group to lead on an innovative campaign and offer support. | Impacts from events will be measured in sales numbers, interactions with campaigns both in person and on social media. | MN005 | Support will also be offered by the Sustainability Team | Before end of toolkit. |  | MN005 - Campaigning and Influencing – Mandatory- The partnership has devised and successfully delivered one or more innovative campaigns on Fairtrade, trade justice or ethical consumption in the last year, which have been run in partnership with students |  |  | Students' Union societies, SU Environment Rep and SU Reps. | Completed
25 - 24/26 | Review Fairtrade Products on Sale and the POS Signage for Fairtrade Fortnight. | Currently Fairtrade products are sold and promoted at both Cardiff Met and Students' Union catering and retail facilities. In past more products have been promoted during Fairtrade Fortnight. | Review any improvement in Fairtrade products sold since the last submission, at catering and retail facilities belonging to both Cardiff Met and the Student's Union. Create specific Fairtrade section in each catering and retail outlet. | Range of products available, volume sold. Review any increase from previous two week period of sales. | MN004, MN006, MN007 and MN008. | Relevant staff and/or students have the time to audit the products sold at the University before Fairtrade Fortnight. | Before 24-26 submission |  | MN004, MN006, MN007 and MN008. |  |  | Relevant Sustainability and SU staff. | Completed
26 - 24/26 | Fairtrade Steering Group to review 2024 survey and republish in time for 24-26 submission | Survey findings from 2022 survey | Fairtrade Steering Group to advertise and encourage the completion of the Fairtrade Survey during Fairtrade Fortnight, Green Week or any other relevant key dates | Review of 2026 survey results for increase in completion, awareness and action of suggestions and improvements identified. Results to be made public. | MN009 | The Fairtrade Steering Group can find volunteers to participate in the completion of the Fairtrade survey with findings made public. | Complete all by end of March 2026 |  | MN009 - - Research and curriculum - Mandatory - Within the last two years the partnership has successfully carried out relevant scoping activities amongst a broad range of its students and/or staff (not just those already engaged in the campaigns) to inform its Fairtrade work, and has made the findings publically available. |  |  | Fairtrade Steering group. | Completed
27 - 24/26 | Opportunities for Students with real world projects. | There are opportunities for students to engage with real projects - specifically Fairtrade | Ensure that the real world projects offered to students include Fairtrade topics. | Students projects outcomes. | MN010 | Routes to engage students with sustainability topics already exist. These routes can be used to offer them opportunities to engage with Fairtrade. | Before end of toolkit. |  | MN010 - Research and curriculum - Mandatory- The partnership provides and publicises opportunities for students to investigate Fairtrade, trade justice or ethical consumption issues on or off-campus within their course work or dissertations |  |  | Fairtrade Steering Group and University academics. | Completed
28 - 24/26 | Create Fairtrade Annual report for 2025-2026 | An Sustainability Report used to be produced annually covering all aspects of Sustainability and the Environment at the University - for this submissio we will only produce a Fairtrade report. | The University's report on Fairtrade will be published on esternal website | Report will be published online and in print. | MN011 | Report to be created based on the last two years of Fairtrade Activity | Annualy |  | MN011 - Outcomes - Mandatory - The partnership publishes an annual progress or impact report on its action on Fairtrade, trade justice and ethical consumption. This should refer to the tasks and progress made through the SMART action plan and should be publically available. This report can be part of a wider sustainability or similar report |  |  | Sustainability Engagement Officer | Completed
29 - 24/26 | SU Fairtrade Policy | An Sustainability Report used to be produced annually covering all aspects of Sustainability and the Environment at the University - for this submissio we will only produce a Fairtrade report. | SU Fairtrade policy to be puclished on external website | SU Fairtrade policy to be puclished on external website | LD001 | Fairtrade Policy to be created to establish support capacity for Fairtrade | 2026-03-01 |  | The students' union has one or more active policies which support Fairtrade passed within the last three years, and has published them online. |  |  | Students Union | Completed
30 - 24/26 | Sustainability Policy mentions Fairtrade | Within the last two years, the partnership has analysed the inclusion of Fairtrade, trade justice and ethical consumption within other cross-cutting institutional and union plans (e.g. procurement plan, sustainability plan, marketing plan) and made suggestions to the relevant stakeholders of how it could be integrated. | Environment and Sustainability Policy 2025 mentions Fairtrade | Published on external website | LD003 | Updated 2025 policy mentions Fairtrade | 2025-05-01 |  | Within the last two years, the partnership has analysed the inclusion of Fairtrade, trade justice and ethical consumption within other cross-cutting institutional and union plans (e.g. procurement plan, sustainability plan, marketing plan) and made suggestions to the relevant stakeholders of how it could be integrated. |  |  | Sustainability Engagement Officer | Completed
31 - 24/26 | Leadership on fairtrade | Support established from new Hrad of Climate Action role | Head of Climate Action to attend Fairtrade Aftternoon Tea event and other awareness opportunitiees, participate in campaigns | Publish support online | LD005 | Support to be widely publicised | 2026-03-01 |  | There is active leadership on Fairtrade, trade justice and ethical consumption issues from one or more senior members of staff or sabbatical officers in the union and institution. |  |  | Sustainability Engagement Officer | Completed
32 - 24/26 | Induction on Fairtrade | Fairtrade has been part of staff and student induction since 2022 | Review induction e-module and sustainability induction slides to include fairtrade | Get number of completed inductions for 24-26 | C1001 | Inductions to be carried out to new staff and every start of new academic year as part of wider sustainaiblity efforts | 2026-03-01 |  | The partnership has included Fairtrade and ethical consumption in staff and student inductions. These inductions should state the organisation's commitment to Fairtrade, provide some information on why Fairtrade is important, and state some tangible actions staff and students can take to fit in with the organisation's values. |  |  | Sustainability Engagement Officer | Completed
33 - 24/26 | Support student group to campaign on Fairtrade | University has done this in previous years also | Identify resources for supporting a student group or society | Measure attendance if it's a campaign with an in person event or online engagement | C1002 | Give realistic budget and time frame for campaign to happen | 2026-03-01 |  | The partnership has supported one or more student groups to campaign on Fairtrade, ethical consumption or trade justice. |  |  | Sustainability Engagement Officer | Completed
34 - 24/26 | Partner with local fairtrade group | .Haven't done this in previous years | Partner with Fairtrade Pontypridd as part of awareness event | Measure attendance | C1004 | Set realistic time frame and comittments | 2026-03-01 |  | Within the last two years, the partnership has partnered with a local off-campus Fairtrade group, and worked together on at least one project or campaign over the year |  |  | Sustainability Engagement Officer | Completed
35 - 24/26 | Collaborate with non fairtrade university | Haven't done this in the past | Organised external meeting with other universitites to establish support | Attendance to extrnal meetings | C1006 | Heavily depended on own university resources | 2026-03-01 |  | Within the last two years, the partnership has proactively collaborated with another aspiring Fairtrade University or College in achieving Fairtrade status and can demonstrate how their involvement has enabled the attainment of the award. This could include encouraging a previously uninvolved university or college to sign up for the next programme cohort. |  |  | Sustainability Engagement Officer | Completed
36 - 24/26 | Fairtrade Presence on external presence | Website presence already established but some out of date elements, working on new website to be launched in 2026 | Update Fairtrade Section | Measured by achievement | C1007 | Resources and materials are available | 2026-03-01 |  | The partnership's work and support of Fairtrade has an effective and up-to-date web presence, which is easily found and well-used. |  |  | Sustainability Engagement Officer | Completed
37 - 24/26 | Fairtrade Social Media | Fairtrade presence on social media already established | Share new campaigns etc of Fairtrade progress | Measurable through online interaction | C1008 | Materials will be created with the help of Sustainability Team in collaboration with students | 2026-03-01 |  | The partnership has utilised social media and other communication channels to communicate Fairtrade campaigns widely and successfully. |  |  | Sustainability Engagement Officer | Completed
38 - 24/26 | Fresher's Fayre Presence | Fairtrade has had a presence at Freshers Fairs in the past 2 years | To have a stall at Freshers Fairs or Refresher | Through attandance | C1010 | Materials and support available | 2026-03-01 |  | The partnership ensures there is a strong Fairtrade presence at Freshers' Fairs (or equivalent) and/or recruitment days. |  |  | Sustainability Team/ SU | Completed
39 - 24/26 | Student Funraiser | Not completed in the past | To support a student group to fundraise for fairtrade | Money raised | C1012 | Materials and support available | 2026-03-01 |  | The partnership has supported student groups or RAG groups to fundraise for the Fairtrade Foundation. |  |  | Sustaianbility Team/ Student Group | Completed
40 - 24/26 | Fairtrade in communal areas | Limited resources to complete in the past | Offer Fairtrade as an option in communal areas and monitor awareness | Measurable to consumption levels and awanress | PL001 | Materials and support available | 2026-03-01 |  | The partnership has proactively engaged staff and publicised Fairtrade widely as an option for communal tea, coffee, hot chocolate and sugar in staff areas and offices. |  |  | Sustainability Team | Completed
41 - 24/26 | Fairtrade Special Discount | Limited discounts offered in past years | To organise a discounted day for specific fairtrade products and advertise widely | Through sales | PL010 | Support available | 2026-03-01 |  | Sales promotions (such as discounts, competitions, loyalty cards etc.) are run on Fairtrade-certified products periodically throughout the year, across relevant retail outlets. |  |  | Sustainability Team / Catering | Completed
42 - 24/26 | Positive Fairtrade Outcomes | Not widely identified in the past | To carry out interviwes to identify positive outcomes across all areas | Yes, through qualitative data | OT001/OT002/OT003 | Support available | 2026-03-01 |  | The partnership has identified positive outcomes for students, institution and community through its Fairtrade work. |  |  | Sustainablity Team | Completed